## Read me
11DP-C · Live Gantt chart and Project Status
Generated on 8 October 2026 from the plan submitted on 9 October (baseline). From then on, update it by hand.
What to edit
Only the yellow cells. Each owner updates their own rows in the Project Status sheet: Real Start, Real Finish, Status, Notes;
the Tasks sheet (Gantt chart), the delays, and the Members totals update from it automatically. Also: Real date and Status (Milestones);
Likelihood, Impact, Status, Last review, Notes (Risks). Planned dates are the 9 October baseline and must not be changed.
Example: when Leo starts task 2.1 on Tue 13 Oct, he writes 13/10/2026 in Real Start (Project Status) and sets Status to 'In progress';
when he finishes, he writes the Real end and sets 'Completed'. Delay is computed automatically (negative = early).
Status values (Formal Requirements, Project Status Document): Backlog, Pending, In progress, Completed, Incident, Canceled.
How to read the chart (Tasks sheet)
Bar fill = phase of the planned task: grey Phase 0 (completed), blue WP1, teal WP2, amber WP3, purple WP4.
Line under the bar = owner: red Aarón, lime Bruno, black Ettore, magenta Leo, azure Pol, grey all members.
● = real execution, drawn from Real start to Real end (or to today while the task is open). Red header cell = today. Shaded columns = holidays.
Adding a task
Insert a row inside its phase, copy a neighbouring task row (formulas and formats follow), and fill ID, Task, Owner, Duration, Effort, Predecessors, Planned start.
A task added after 9 October is new scope: write 'Added on <date>' in Notes so the final retrospective can explain it.
Sheets
Project Status: the live status document (Formal Requirements III), where real dates, status, and notes are entered · Tasks: Gantt grid, planned vs real · Members: tasks and effort per member · Milestones · Risks · Holidays.
Class sessions (bottom of the Tasks grid): Pres = Project presentation and access to GitHub · Ref = Paper structure, sources and references · SB = Structural biology · PDB = PDB lab · Gen = Genomics · SA1 = Sequence alignment lab 1 · SA2 = Sequence alignment lab 2 · IBR = Integrated bioinformatics reasoning · SSP = Structure superposition lab · Ret = Project retrospective (online, optional) · Def = Project defence.
Yellow = cell to edit

## Project Status
Project Status · Group 11DP-C · Pyruvate Kinase Deficiency
Task tracking — Updated up to | 2026-10-26 | Edit only the yellow cells of your own tasks: Real Start, Real Finish, Status, Notes. Planned dates come from the 9 October baseline.
Task | Resp. | Plan. Start Date | Plan. Finish Date | Real Start Date | Real Finish Date | Status | Notes
Phase 0 · Project start-up (completed)
0.1 Create the GitHub repository and write the README | Leo | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | Completed | Evidence: Commits of 17 Sep.
0.2 Create the report file and the folder structure | Ettore | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | Completed | Evidence: Commits of 17 Sep.
0.3 Study the course instructions and the disease | All | 2026-09-21 | 2026-10-08 | 2026-09-21 | 2026-10-08 | Completed | Evidence: Reported by the team.
0.4 Team meeting 1 (after class) | All | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | Completed | Evidence: Reported by the team.
0.5 Format the report file | Aarón | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | Completed | Evidence: Commit of 28 Sep.
0.6 Team meeting 2 (after class) | All | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | Completed | Evidence: Reported by the team.
0.7 Team meeting 3 (after class) | All | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Completed | Evidence: Reported by the team.
0.8 Draft the project plan (introduction, objectives, Gantt chart, risks) | Ettore | 2026-10-05 | 2026-10-08 | 2026-10-05 | 2026-10-08 | Completed | Evidence: Draft files.
0.9 Team meeting 4 (after class): review of the draft plan; decision to submit it through GitHub rather than as a PDF | All | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2026-10-08 | Completed | Evidence: Reported by the team.
WP1 · Project management and GitHub
1.1 Review and commit the introduction (PKD_1); create the folders report/, status/, gantt/, and references/ | Ettore | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | Completed | Introduction committed by Ettore on 9 Oct; the folders gantt/, status/, references/, and report/ were created by Leo and Bruno on 8 Oct.
1.2 Review and commit the overview and team section (PKD_2); submit the repository URL on Moodle | Aarón | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Completed | PKD_2 committed by Aarón on 8 Oct; repository URL submitted on Moodle by Ettore on 9 Oct.
1.3 Review and commit the Gantt chart (PKD_3) | Bruno | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-08 | Completed | Committed by Leo on 8 Oct and edited by Pol; owner after the role swap: Bruno.
1.4 Review and commit the task details (PKD_4) | Pol | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-08 | Completed | Committed by Pol on 8 Oct; owner columns corrected for the role swap.
1.5 Review and commit the risk analysis and references (PKD_5, PKD_6) | Leo | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Completed | Committed by Bruno (PKD_6 on 8 Oct, PKD_5 on 9 Oct), references updated by Ettore on 9 Oct; owner after the role swap: Leo.
1.6 Create the Project Status document | Ettore | 2026-10-13 | 2026-10-13 | 2026-10-09 | 2026-10-09 | Completed | Created by Ettore on 9 Oct (status/Project_Status_2026_10_09.md).
1.7 Weekly status update and team meeting (Fridays 16 and 23 Oct) | Ettore | 2026-10-16 | 2026-10-23 | 2026-10-16 | 2026-10-23 | Completed | Meetings of 16 and 23 Oct held.
1.8 Prepare the Project Status document for the 22 Oct discussion | Ettore | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-10-20 | Completed | Project Status of 20 Oct, discussed in class on 22 Oct.
1.9 Produce the final Gantt chart with real dates (live version) | Ettore | 2026-10-27 | 2026-10-27 | 2026-10-26 | 2026-10-26 | Completed | Final Gantt chart and Project Status of 26 Oct (gantt/ and status/).
WP2 · Data sources, literature, and sequences
2.1 Characterize the supplied sequences: translate both CDSs, compare wild type and mutant, and name the variant in HGVS nomenclature | Bruno | 2026-10-13 | 2026-10-13 | 2026-10-23 | 2026-10-24 | Completed | Both CDSs translated; one difference, c.1456C>T, p.(Arg486Trp).
2.2 Identify the gene, the isoform, and the reference entries (HGNC, NCBI Gene, UniProt) | Leo | 2026-10-13 | 2026-10-13 | 2026-10-24 | 2026-10-24 | Completed | Reference records in analysis/sequence/raw/.
2.3 Collect clinical and population evidence on the variant (ClinVar, gnomAD, OMIM, literature) | Leo | 2026-10-15 | 2026-10-16 | 2026-10-24 | 2026-10-24 | Completed | ClinVar and gnomAD evidence; Table 1.
2.4 Review the literature on PK and PKD: normal function, mechanism, inheritance, and clinical features | Aarón | 2026-10-13 | 2026-10-15 | 2026-10-23 | 2026-10-26 | Completed | Sources of the Background checked; cited articles saved in references/articles/ by Aarón.
2.5 Retrieve the reviewed orthologous sequences: rat, mouse, and dog (outgroup) | Leo | 2026-10-14 | 2026-10-14 | 2026-10-24 | 2026-10-24 | Completed | Rat, mouse, and dog PKLR and the vertebrate panel.
2.6 Select the experimental structures: wild-type and mutant human R-type PK; rat PK | Pol | 2026-10-13 | 2026-10-13 | 2026-10-24 | 2026-10-26 | Completed | Wild-type PDB 2VGB and mutant PDB 2VGI; no rat structure used (see 3.5).
2.7 Archive the sources in references/ and maintain the reference list | Leo | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-26 | Completed | Reference list completed; database records in references/databases/.
2.8 Verify the sequence characterization independently: repeat the translation and the comparison of the four files | Ettore | 2026-10-14 | 2026-10-14 | 2026-10-24 | 2026-10-24 | Completed | Translation, variant, and identities recomputed by independent methods: all agree.
WP3 · Sequence and structure analysis
3.1 Pairwise alignments of human PK with the rat and mouse orthologs (protein and CDS) | Bruno | 2026-10-15 | 2026-10-15 | 2026-10-23 | 2026-10-24 | Completed | Human PKLR vs rat, mouse, and dog: protein identity 91.1%, 91.6%, 92.5%.
3.2 Multiple sequence alignment of human, rat, mouse, and dog PK; conservation of the substituted position and lineage of each difference | Bruno | 2026-10-16 | 2026-10-19 | 2026-10-24 | 2026-10-24 | Completed | Multiple alignments; residue 486 by species; Figure 1, Table 2.
3.3 Map the substituted residue on the wild-type structure: distances to the active site, the allosteric site, and the domain and subunit interfaces | Pol | 2026-10-14 | 2026-10-15 | 2026-10-24 | 2026-10-24 | Completed | Arg486 in the C domain; distances to the FBP and active sites.
3.4 Superpose the wild-type and mutant structures (repeated in the 22 Oct lab) | Pol | 2026-10-16 | 2026-10-19 | 2026-10-24 | 2026-10-24 | Completed | Wild-type and R486W structures superposed.
3.5 Compare the human R-type and rat L-type structures around the substituted position | Pol | 2026-10-20 | 2026-10-20 | 2026-10-24 |  | Canceled | Not done: no functional data exist on the rat enzyme at this position or on Gln at 486 in humans, so a structural comparison could not be interpreted in terms of function.
3.6 Assess pathogenicity: combine clinical, population, conservation, structural, and biochemical evidence | Aarón | 2026-10-19 | 2026-10-19 | 2026-10-26 | 2026-10-26 | Completed | Done in the Results and Discussion of the report (Discussion written by Ettore).
3.7 Explain the impact on the patient: from enzyme activity to red-cell ATP, haemolysis, and clinical severity | Aarón | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-26 | Completed | Done in the Discussion of the report (written by Ettore).
3.8 Team synthesis meeting: from variant to patient | Ettore | 2026-10-21 | 2026-10-21 | 2026-10-25 | 2026-10-25 | Completed | Synthesis meeting held on 25 Oct.
3.9 Verify the alignments independently: repeat the multiple sequence alignment and check the residue at the substituted position in every species | Leo | 2026-10-20 | 2026-10-20 | 2026-10-24 | 2026-10-24 | Completed | Residue 486 checked across vertebrate PKLR orthologues.
3.10 Re-run all analyses with the course tools (BLAST, Clustal Omega, PyMOL) to confirm the data and to practise every phase | All | 2026-10-25 | 2026-10-26 | 2026-10-25 | 2026-10-26 | Completed | Added on 25 Oct: all analyses re-run by every member to confirm the data and to practise every phase of the project.
3.11 Revise the Lab 1 notebook with the PKLR records of rat and mouse | Pol | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Completed | Added on 26 Oct: lab/Lab_1_.md rewritten with rat XM_006232593.6 / P12928 and mouse NM_013631.2 / P53657, replacing the PKM screenshots.
WP4 · Report, delivery, and defence
4.1 Write the Background | Aarón | 2026-10-21 | 2026-10-22 | 2026-10-24 | 2026-10-26 | Completed | report/sections/report_background.md.
4.2 Write the Methods | Leo | 2026-10-21 | 2026-10-22 | 2026-10-26 | 2026-10-26 | Completed | report/sections/report_methods.md and report_references.md.
4.3 Write the Results on sequences and species comparison | Bruno | 2026-10-20 | 2026-10-21 | 2026-10-26 | 2026-10-26 | Completed | Results on the variant (report_results_cause.md) and on the species comparison (report_results_species.md).
4.4 Write the Results on structures; prepare the figures | Pol | 2026-10-21 | 2026-10-22 | 2026-10-26 | 2026-10-26 | Completed | report/sections/report_results_structure.md; Figures 1 and 2.
4.5 Write the Discussion and Conclusions | Ettore | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-26 | Completed | report/sections/report_discussion.md and report_conclusions.md.
4.6 Write the Abstract and assemble the report | Aarón | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Completed | Abstract, Abbreviations, and Declarations written by Aarón; report assembled and committed by Ettore (report/report.md).
4.7 Coordinate the full read-through and corrections | Bruno | 2026-10-27 | 2026-10-27 | 2026-10-26 | 2026-10-26 | Completed | Read-through by all members.
4.8 Check the format limits and the references | Leo | 2026-10-27 | 2026-10-27 | 2026-10-26 | 2026-10-26 | Completed | Format limits and references checked by all members.
4.9 Deliver the final report on GitHub | Aarón | 2026-10-28 | 2026-10-28 | 2026-10-26 | 2026-10-26 | Completed | README with the link to the final report committed by Aarón; repository URL submitted on Moodle by Ettore.
4.10 Prepare the defence slides on the background and the impact on the patient | Aarón | 2026-10-29 | 2026-10-29 |  |  | Pending
4.11 Prepare the defence slides on the data sources and methods | Leo | 2026-10-29 | 2026-10-29 |  |  | Pending
4.12 Prepare the defence slides on the discussion and conclusions | Ettore | 2026-10-29 | 2026-10-29 |  |  | Pending
4.13 Prepare the defence slides on the sequence and species-comparison results | Bruno | 2026-10-29 | 2026-10-29 |  |  | Pending
4.14 Prepare the defence slides on the structural results | Pol | 2026-10-29 | 2026-10-29 |  |  | Pending
4.15 Assemble the defence presentation: unify the format and confirm who presents each part | Leo | 2026-10-30 | 2026-10-30 |  |  | Pending
4.16 Coordinate the defence rehearsal, with cross-questioning between members | Bruno | 2026-11-02 | 2026-11-03 |  |  | Pending
Legend
Canceled | Will not be done; explain why in Notes
Completed | Finished; Real Finish Date filled
Incident | A problem occurred; describe it and the workaround in Notes
In progress | Started; Real Start Date filled
Backlog | Contingency task, done only if needed
Pending | Planned, not started
Red real date = later than planned. Red planned finish = past the update date while the task is still open.

## Tasks
11DP-C · Pyruvate Kinase Deficiency: from a PKLR variant to haemolytic anaemia · live Gantt chart and Project Status
Planned dates = baseline of 9 October 2026. Real dates and status are read from the Project Status sheet: edit them there, not here. Bar fill = phase (planned); line under the bar = owner; ● = real execution.
[13 empty] | 2026-09-14 |  | 2026-09-21 |  |  |  |  | 2026-09-28 |  |  |  |  | 2026-10-05 |  |  |  |  | 2026-10-12 |  |  |  |  | 2026-10-19 |  |  |  |  | 2026-10-26 |  |  |  |  | 2026-11-02
ID | Phase | Task | Owner | Duration (working days) | Effort (days) | Predecessors | Planned start | Planned end | Real start | Real end | Status | Delay (working days) | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | Output and completion criterion (baseline)
P0 | P0 | Phase 0 · Project start-up (completed) |  | 15 |  |  | 2026-09-17 | 2026-10-08
0.1 | P0 | Create the GitHub repository and write the README | Leo | 1 | 1 |  | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | Completed | 0 | [36 empty] | Output: Repository 11DP-C_Pyruvate-Kinase-Deficiency_IB_2026. Evidence: Commits of 17 Sep. | bar: 2026-09-17
0.2 | P0 | Create the report file and the folder structure | Ettore | 1 | 1 |  | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | Completed | 0 | [36 empty] | Output: `report.md`, `figures/`. Evidence: Commits of 17 Sep. | bar: 2026-09-17
0.3 | P0 | Study the course instructions and the disease | All | 13 | 13 |  | 2026-09-21 | 2026-10-08 | 2026-09-21 | 2026-10-08 | Completed | 0 | [36 empty] | Output: Shared understanding of the task. Evidence: Reported by the team. | bar: 2026-09-21 to 2026-09-23; 2026-09-25 to 2026-10-08
0.4 | P0 | Team meeting 1 (after class) | All | 1 | 1 |  | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | Completed | 0 | [36 empty] | Output: Organization of the work. Evidence: Reported by the team. | bar: 2026-09-21
0.5 | P0 | Format the report file | Aarón | 1 | 1 |  | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | Completed | 0 | [36 empty] | Output: Formatted `report.md`. Evidence: Commit of 28 Sep. | bar: 2026-09-28
0.6 | P0 | Team meeting 2 (after class) | All | 1 | 1 |  | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | Completed | 0 | [36 empty] | Output: Organization of the work. Evidence: Reported by the team. | bar: 2026-09-28
0.7 | P0 | Team meeting 3 (after class) | All | 1 | 1 |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Completed | 0 | [36 empty] | Output: Organization of the work. Evidence: Reported by the team. | bar: 2026-10-05
0.8 | P0 | Draft the project plan (introduction, objectives, Gantt chart, risks) | Ettore | 4 | 4 |  | 2026-10-05 | 2026-10-08 | 2026-10-05 | 2026-10-08 | Completed | 0 | [36 empty] | Output: Draft plan, sections PKD_1 to PKD_6. Evidence: Draft files. | bar: 2026-10-05 to 2026-10-08
0.9 | P0 | Team meeting 4 (after class): review of the draft plan; decision to submit it through GitHub rather than as a PDF | All | 1 | 1 |  | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2026-10-08 | Completed | 0 | [36 empty] | Output: Agreed plan and submission format. Evidence: Reported by the team. | bar: 2026-10-08
WP1 | WP1 | WP1 · Project management and GitHub |  | 12 |  |  | 2026-10-09 | 2026-10-27
1.1 | WP1 | Review and commit the introduction (PKD_1); create the folders report/, status/, gantt/, and references/ | Ettore | 1 | 1 |  | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-10-09 | Completed | 0 | [36 empty] | Output: Introduction and required folders in the repository. Accomplished when: The four required folders exist and the introduction is committed by its reviewer. | bar: 2026-10-09
1.2 | WP1 | Review and commit the overview and team section (PKD_2); submit the repository URL on Moodle | Aarón | 1 | 1 | 1.1 | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Completed | 0 | [36 empty] | Output: PKD_2 committed; URL submitted. Accomplished when: The URL is submitted on Moodle by 9 Oct. | bar: 2026-10-08 to 2026-10-09
1.3 | WP1 | Review and commit the Gantt chart (PKD_3) | Bruno | 1 | 1 | 1.1 | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-08 | Completed | -1 | [36 empty] | Output: PKD_3 committed. Accomplished when: The chart renders on GitHub and its dates match PKD_4. | bar: 2026-10-08
1.4 | WP1 | Review and commit the task details (PKD_4) | Pol | 1 | 1 | 1.1 | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-08 | Completed | -1 | [36 empty] | Output: PKD_4 committed. Accomplished when: Every task has an owner, output, duration, predecessor, and completion criterion. | bar: 2026-10-08
1.5 | WP1 | Review and commit the risk analysis and references (PKD_5, PKD_6) | Leo | 1 | 1 | 1.1 | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Completed | 0 | [36 empty] | Output: PKD_5 and PKD_6 committed. Accomplished when: Each risk has a score and a contingency plan; every citation has a reference. | bar: 2026-10-08 to 2026-10-09
1.6 | WP1 | Create the Project Status document | Ettore | 1 | 1 | 1.2 | 2026-10-13 | 2026-10-13 | 2026-10-09 | 2026-10-09 | Completed | -1 | [36 empty] | Output: `status/` document. Accomplished when: It lists every task with owner, planned dates, real dates, status, and notes. | bar: 2026-10-09
1.7 | WP1 | Weekly status update and team meeting (Fridays 16 and 23 Oct) | Ettore | 6 | 2 | 1.6 | 2026-10-16 | 2026-10-23 | 2026-10-16 | 2026-10-23 | Completed | 0 | [36 empty] | Output: Dated notes in `status/`. Accomplished when: After each meeting, real dates, status changes, and incidents are recorded. | bar: 2026-10-16 to 2026-10-23
1.8 | WP1 | Prepare the Project Status document for the 22 Oct discussion | Ettore | 1 | 1 | 1.6 | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-10-20 | Completed | 0 | [36 empty] | Output: Updated `status/` document. Accomplished when: Planned and real dates, status, and notes are current on 20 Oct. | bar: 2026-10-20
1.9 | WP1 | Produce the final Gantt chart with real dates (live version) | Ettore | 1 | 1 | 4.6 | 2026-10-27 | 2026-10-27 | 2026-10-26 | 2026-10-26 | Completed | -1 | [36 empty] | Output: Final Gantt chart in `gantt/`. Accomplished when: Every task shows its real dates, and deviations are explained. | bar: 2026-10-26
WP2 | WP2 | WP2 · Data sources, literature, and sequences |  | 5 |  |  | 2026-10-13 | 2026-10-19
2.1 | WP2 | Characterize the supplied sequences: translate both CDSs, compare wild type and mutant, and name the variant in HGVS nomenclature | Bruno | 1 | 1 | 1.3 | 2026-10-13 | 2026-10-13 | 2026-10-23 | 2026-10-24 | Completed | 8 | [36 empty] | Output: Variant table (DNA and protein level). Accomplished when: Every difference is listed at DNA and protein level and verified by a second member (task 2.8). | bar: 2026-10-23
2.2 | WP2 | Identify the gene, the isoform, and the reference entries (HGNC, NCBI Gene, UniProt) | Leo | 1 | 1 | 1.5 | 2026-10-13 | 2026-10-13 | 2026-10-24 | 2026-10-24 | Completed | 8 | [36 empty] | Output: Table of identifiers. Accomplished when: The gene symbol, isoform, and accession numbers are recorded with access dates.
2.3 | WP2 | Collect clinical and population evidence on the variant (ClinVar, gnomAD, OMIM, literature) | Leo | 2 | 2 | 2.1, 2.5 | 2026-10-15 | 2026-10-16 | 2026-10-24 | 2026-10-24 | Completed | 5 | [36 empty] | Output: Evidence table with sources. Accomplished when: Classification, allele frequency, and published functional data are recorded with sources.
2.4 | WP2 | Review the literature on PK and PKD: normal function, mechanism, inheritance, and clinical features | Aarón | 3 | 3 | 1.2 | 2026-10-13 | 2026-10-15 | 2026-10-23 | 2026-10-26 | Completed | 7 | [36 empty] | Output: Annotated literature notes. Accomplished when: Each statement planned for the Background has at least one primary or review source. | bar: 2026-10-23 to 2026-10-26
2.5 | WP2 | Retrieve the reviewed orthologous sequences: rat, mouse, and dog (outgroup) | Leo | 1 | 1 | 2.2 | 2026-10-14 | 2026-10-14 | 2026-10-24 | 2026-10-24 | Completed | 7 | [36 empty] | Output: FASTA files and accession list. Accomplished when: Every sequence is saved in the repository with its accession number.
2.6 | WP2 | Select the experimental structures: wild-type and mutant human R-type PK; rat PK | Pol | 1 | 1 | 1.4 | 2026-10-13 | 2026-10-13 | 2026-10-24 | 2026-10-26 | Completed | 9 | [36 empty] | Output: Table of PDB entries (method, resolution, construct). Accomplished when: One wild-type and one mutant entry are chosen, with the reasons recorded. | bar: 2026-10-26
2.7 | WP2 | Archive the sources in references/ and maintain the reference list | Leo | 1 | 1 | 2.3, 2.4 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-26 | Completed | 5 | [36 empty] | Output: PDFs and Mini Oxford reference list. Accomplished when: Every cited source is archived and listed in the required style. | bar: 2026-10-26
2.8 | WP2 | Verify the sequence characterization independently: repeat the translation and the comparison of the four files | Ettore | 1 | 1 | 2.1 | 2026-10-14 | 2026-10-14 | 2026-10-24 | 2026-10-24 | Completed | 7 | [36 empty] | Output: Verification note. Accomplished when: The variant table of task 2.1 is confirmed, or each discrepancy is resolved with its owner.
WP3 | WP3 | WP3 · Sequence and structure analysis |  | 9 |  |  | 2026-10-14 | 2026-10-26
3.1 | WP3 | Pairwise alignments of human PK with the rat and mouse orthologs (protein and CDS) | Bruno | 1 | 1 | 2.1, 2.5 | 2026-10-15 | 2026-10-15 | 2026-10-23 | 2026-10-24 | Completed | 6 | [36 empty] | Output: Alignments and identity table. Accomplished when: Percent identity and similarity are reported for each pair, with tool and parameters. | bar: 2026-10-23
3.2 | WP3 | Multiple sequence alignment of human, rat, mouse, and dog PK; conservation of the substituted position and lineage of each difference | Bruno | 2 | 2 | 3.1 | 2026-10-16 | 2026-10-19 | 2026-10-24 | 2026-10-24 | Completed | 4 | [36 empty] | Output: Alignment figure and conservation notes. Accomplished when: The residue at the substituted position is reported for every species, and the lineage of each change is stated.
3.3 | WP3 | Map the substituted residue on the wild-type structure: distances to the active site, the allosteric site, and the domain and subunit interfaces | Pol | 2 | 2 | 2.1, 2.6 | 2026-10-14 | 2026-10-15 | 2026-10-24 | 2026-10-24 | Completed | 6 | [36 empty] | Output: Annotated structure figure and distance table. Accomplished when: Distances are measured in a stated structure and chain.
3.4 | WP3 | Superpose the wild-type and mutant structures (repeated in the 22 Oct lab) | Pol | 2 | 2 | 3.3 | 2026-10-16 | 2026-10-19 | 2026-10-24 | 2026-10-24 | Completed | 4 | [36 empty] | Output: Superposition figure and RMSD values. Accomplished when: Global and local differences are quantified with the method stated.
3.5 | WP3 | Compare the human R-type and rat L-type structures around the substituted position | Pol | 1 | 1 | 3.4, 3.2 | 2026-10-20 | 2026-10-20 | 2026-10-24 |  | Canceled | [37 empty] | Output: Comparison figure and notes. Accomplished when: The local environment of the position is described in both species. | bar: 2026-10-26
3.6 | WP3 | Assess pathogenicity: combine clinical, population, conservation, structural, and biochemical evidence | Aarón | 1 | 1 | 2.3, 2.4, 3.1 | 2026-10-19 | 2026-10-19 | 2026-10-26 | 2026-10-26 | Completed | 5 | [36 empty] | Output: Evidence summary table. Accomplished when: Each line of evidence is classified as measured result, hypothesis, or open question. | bar: 2026-10-26
3.7 | WP3 | Explain the impact on the patient: from enzyme activity to red-cell ATP, haemolysis, and clinical severity | Aarón | 1 | 1 | 3.6 | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-26 | Completed | 4 | [36 empty] | Output: One-page causal summary. Accomplished when: Each step from variant to clinical picture is supported by a cited source or our own result. | bar: 2026-10-26
3.8 | WP3 | Team synthesis meeting: from variant to patient | Ettore | 1 | 1 | 3.5, 3.7, 3.9 | 2026-10-21 | 2026-10-21 | 2026-10-25 | 2026-10-25 | Completed | 2 | [36 empty] | Output: Meeting notes. Accomplished when: Every member can explain the full chain from variant to patient.
3.9 | WP3 | Verify the alignments independently: repeat the multiple sequence alignment and check the residue at the substituted position in every species | Leo | 1 | 1 | 3.2 | 2026-10-20 | 2026-10-20 | 2026-10-24 | 2026-10-24 | Completed | 3 | [36 empty] | Output: Verification note. Accomplished when: The residues reported in task 3.2 are confirmed, or each discrepancy is resolved with its owner.
3.10 | WP3 | Re-run all analyses with the course tools (BLAST, Clustal Omega, PyMOL) to confirm the data and to practise every phase | All | 1 | 1 | 3.9 | 2026-10-25 | 2026-10-26 | 2026-10-25 | 2026-10-26 | Completed | 0 | [36 empty] | Output: Verification note. Accomplished when: The residues reported in task 3.2 are confirmed, or each discrepancy is resolved with its owner. | bar: 2026-10-26
3.11 | WP3 | Revise the Lab 1 notebook with the PKLR records of rat and mouse | Pol | 1 | 1 | 3.1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Completed | 0 | [36 empty] | Output: Verification note. Accomplished when: The residues reported in task 3.2 are confirmed, or each discrepancy is resolved with its owner. | bar: 2026-10-26
WP4 | WP4 | WP4 · Report, delivery, and defence |  | 11 |  |  | 2026-10-20 | 2026-11-03
4.1 | WP4 | Write the Background | Aarón | 2 | 2 | 2.4 | 2026-10-21 | 2026-10-22 | 2026-10-24 | 2026-10-26 | Completed | 2 | [36 empty] | Output: Background section in `report/`. Accomplished when: It states the problem and the question, with every claim cited. | bar: 2026-10-26
4.2 | WP4 | Write the Methods | Leo | 2 | 2 | 2.7, 3.9 | 2026-10-21 | 2026-10-22 | 2026-10-26 | 2026-10-26 | Completed | 2 | [36 empty] | Output: Methods section in `report/`. Accomplished when: Another student could reproduce every analysis from it. | bar: 2026-10-26
4.3 | WP4 | Write the Results on sequences and species comparison | Bruno | 2 | 2 | 3.2 | 2026-10-20 | 2026-10-21 | 2026-10-26 | 2026-10-26 | Completed | 3 | [36 empty] | Output: Results, part 1. Accomplished when: It reports what was measured, without interpretation, with numbered figures or tables. | bar: 2026-10-26
4.4 | WP4 | Write the Results on structures; prepare the figures | Pol | 2 | 2 | 3.5 | 2026-10-21 | 2026-10-22 | 2026-10-26 | 2026-10-26 | Completed | 2 | [36 empty] | Output: Results, part 2; figures. Accomplished when: Figures are numbered, captioned, and stored in the repository. | bar: 2026-10-26
4.5 | WP4 | Write the Discussion and Conclusions | Ettore | 2 | 2 | 3.8 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-26 | Completed | 1 | [36 empty] | Output: Discussion and Conclusions. Accomplished when: They answer the project question and state the limitations. | bar: 2026-10-26
4.6 | WP4 | Write the Abstract and assemble the report | Aarón | 1 | 1 | 4.1, 4.2, 4.3, 4.4, 4.5 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Completed | 0 | [36 empty] | Output: Complete report. Accomplished when: All BMC sections are present; the Abstract has at most 350 words. | bar: 2026-10-26
4.7 | WP4 | Coordinate the full read-through and corrections | Bruno | 1 | 1 | 4.6 | 2026-10-27 | 2026-10-27 | 2026-10-26 | 2026-10-26 | Completed | -1 | [36 empty] | Output: Corrected report. Accomplished when: Every member has read the whole report and all comments are resolved. | bar: 2026-10-26
4.8 | WP4 | Check the format limits and the references | Leo | 1 | 1 | 4.6 | 2026-10-27 | 2026-10-27 | 2026-10-26 | 2026-10-26 | Completed | -1 | [36 empty] | Output: Completed checklist. Accomplished when: At most 7 pages or 5 000 words and five figures or tables; references in Mini Oxford style. | bar: 2026-10-26
4.9 | WP4 | Deliver the final report on GitHub | Aarón | 1 | 1 | 4.7, 4.8, 1.9 | 2026-10-28 | 2026-10-28 | 2026-10-26 | 2026-10-26 | Completed | -2 | [36 empty] | Output: Final repository. Accomplished when: All files are committed before the deadline. | bar: 2026-10-26
4.10 | WP4 | Prepare the defence slides on the background and the impact on the patient | Aarón | 1 | 1 | 4.9 | 2026-10-29 | 2026-10-29 |  |  | Pending | [37 empty] | Output: Slides, part 1. Accomplished when: The slides cover the Background and SO3, and their presenter is named.
4.11 | WP4 | Prepare the defence slides on the data sources and methods | Leo | 1 | 1 | 4.9 | 2026-10-29 | 2026-10-29 |  |  | Pending | [37 empty] | Output: Slides, part 2. Accomplished when: The slides cover the Methods, and their presenter is named.
4.12 | WP4 | Prepare the defence slides on the discussion and conclusions | Ettore | 1 | 1 | 4.9 | 2026-10-29 | 2026-10-29 |  |  | Pending | [37 empty] | Output: Slides, part 3. Accomplished when: The slides answer the project question and state the limitations.
4.13 | WP4 | Prepare the defence slides on the sequence and species-comparison results | Bruno | 1 | 1 | 4.9 | 2026-10-29 | 2026-10-29 |  |  | Pending | [37 empty] | Output: Slides, part 4. Accomplished when: The slides cover SO1 and SO4 results, and their presenter is named.
4.14 | WP4 | Prepare the defence slides on the structural results | Pol | 1 | 1 | 4.9 | 2026-10-29 | 2026-10-29 |  |  | Pending | [37 empty] | Output: Slides, part 5. Accomplished when: The slides cover SO2 results, and their presenter is named.
4.15 | WP4 | Assemble the defence presentation: unify the format and confirm who presents each part | Leo | 1 | 1 | 4.10, 4.11, 4.12, 4.13, 4.14 | 2026-10-30 | 2026-10-30 |  |  | Pending | [37 empty] | Output: Complete presentation. Accomplished when: One presentation in a single format, with every member presenting a part.
4.16 | WP4 | Coordinate the defence rehearsal, with cross-questioning between members | Bruno | 2 | 2 | 4.15 | 2026-11-02 | 2026-11-03 |  |  | Pending | [37 empty] | Output: Rehearsal and list of likely questions. Accomplished when: Every member can answer questions on every part of the project.
|  | Milestones | [10 empty] | 2026-09-17: ◆ M0; 2026-10-09: ◆ M1; 2026-10-19: ◆ M2; 2026-10-21: ◆ M3; 2026-10-22: ◆ M4; 2026-10-26: ◆ M5; 2026-10-28: ◆ M6; 2026-11-05: ◆ M7
|  | Class sessions | [10 empty] | 2026-09-17: Pres; 2026-09-21: Ref; 2026-09-28: SB; 2026-10-01: PDB; 2026-10-05: Gen; 2026-10-08: SA1; 2026-10-15: SA2; 2026-10-19: IBR; 2026-10-22: SSP; 2026-10-26: Ret; 2026-11-05: Def
Class sessions: Pres = Project presentation and access to GitHub · Ref = Paper structure, sources and references · SB = Structural biology · PDB = PDB lab · Gen = Genomics · SA1 = Sequence alignment lab 1 · SA2 = Sequence alignment lab 2 · IBR = Integrated bioinformatics reasoning · SSP = Structure superposition lab · Ret = Project retrospective (online, optional) · Def = Project defence
|  | helper: holiday flag (hidden) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on E4: Calendar span of the task in working days (bar length).
Note on F4: Working days of effort. Equals the duration, except 1.7 (two weekly meetings).
Note on M4: Working days between planned and real end; negative = finished early.
Note on N65: Project presentation and access to GitHub
Note on P65: Paper structure, sources and references
Note on U65: Structural biology
Note on X65: PDB lab
Note on Z65: Genomics
Note on AC65: Sequence alignment lab 1
Note on AH65: Sequence alignment lab 2
Note on AJ65: Integrated bioinformatics reasoning
Note on AM65: Structure superposition lab
Note on AO65: Project retrospective (online, optional)
Note on AW65: Project defence

## Members
Members, roles, and distribution of the planned work (formulas read the Tasks sheet; Phase 0 excluded)
Owner | Full name | Role | Tasks owned | Effort (working days) | Completed | In progress | Incidents | GitHub username
Aarón | Aarón Godino Martínez | Product Owner | 8 | 11 | 7 | 0 | 0 | Idonthaveanyideafornames
Bruno | Bruno Carrasquilla | Sequence Analyst | 8 | 11 | 6 | 0 | 0 | BrunoCarrasquilla
Ettore | Ettore Colombo | Project Manager | 9 | 11 | 8 | 0 | 0 | AIHector
Leo | Leo Nader Al Hourani | Data and GitHub Manager | 10 | 12 | 8 | 0 | 0 | XxNaderTheKing08Xx
Pol | Pol Monllau | Structure Analyst | 8 | 11 | 6 | 0 | 0 | polmonllau
Total |  |  | 43 | 56 | 35 | 0 | 0

## Milestones
ID | Milestone | Planned date | Real date | Status | Source | Delay (working days)
M0 | Project presented; repository created | 2026-09-17 | 2026-09-17 | Completed | Overview; commits | 0
M1 | Project plan submitted | 2026-10-09 | 2026-10-09 | Completed | Overview | 0
M2 | Data collected (variant, sequences, structures, literature) | 2026-10-19 | 2026-10-26 | Completed | after 2.7 | 5
M3 | Analyses completed | 2026-10-21 | 2026-10-25 | Completed | after 3.8 | 2
M4 | Project Status document discussed | 2026-10-22 | 2026-10-22 | Completed | Overview; Formal Requirements | 0
M5 | Report draft complete | 2026-10-26 | 2026-10-26 | Completed | after 4.6 | 0
M6 | Final report delivered | 2026-10-28 | 2026-10-26 | Completed | Overview | -2
M7 | Oral defence (all members) | 2026-11-05 |  | Pending | Course schedule
Formulas:
Delay (working days) = IF([Real date]="","",IF([Real date]>=[Planned date],NETWORKDAYS([Planned date],[Real date],Holidays!$A2:A40)-1,-(NETWORKDAYS([Real date],[Planned date],Holidays!$A2:A40)-1)))

## Risks
Risk register · Risk = Likelihood × Impact (1–3 each) · 1–2 Low · 3–5 Medium · 6–9 High
ID | Risk | Likelihood | Impact | Score | Level | Owner | Status | Contingency plan | Last review | Notes
R1 | GitHub unavailable or access problems near a deadline | 2 | 3 | 6 | High | Ettore | Open | Finish each delivery one day early; local clone on every computer; commit after every work session; tell the instructors with evidence of the outage. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R2 | Public databases (UniProt, PDB, NCBI) unavailable, or their records updated or superseded during the project | 2 | 3 | 6 | High | Bruno | Open | Record every accession with its access date; archive the files used in the repository; check the current record before citing; use a mirror or an alternative database. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R3 | Illness or unforeseen personal circumstances make a member unavailable | 2 | 3 | 6 | High | Pol | Open | A second member knows the status of every task; tasks documented in the Project Status; pending tasks redistributed at the weekly meeting; Gantt chart updated. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R4 | Exams and deadlines from other courses overlap with the project period | 3 | 2 | 6 | High | Leo | Open | Collect each member's exam dates; schedule heavy tasks away from them; two days of margin before each delivery; rebalance tasks when a conflict appears. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R5 | Online analysis tools or servers (alignment, structure viewers) unavailable, overloaded, or changed | 2 | 2 | 4 | Medium | Aarón | Open | Run each analysis soon after its lab; know an alternative tool; save inputs and parameters; export every result to the repository. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R6 | Little published evidence, or no experimental structures, for the variants or species studied; articles behind paywalls | 2 | 2 | 4 | Medium | Pol | Open | Search early; university library access; open-access articles and reviews for context; predicted structures, stated as such; justify any topic left out. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R7 | Course requirements, deadlines, or instructions changed or clarified during the project | 1 | 3 | 3 | Medium | Ettore | Open | Check announcements and documents at every weekly meeting; ask the instructors about ambiguities; record confirmed dates; adapt the plan. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R8 | A practical session (8, 15, or 22 October) cancelled or rescheduled | 1 | 2 | 2 | Low | Leo | Open | Learn the method from the course materials and tutoring hours; move the dependent task to the first available date. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).
R9 | Failure of a member's computer or internet connection | 2 | 1 | 2 | Low | Aarón | Open | Keep all work in the remote repository; use university computers or a teammate's device; reassign the affected task if needed. | 2026-10-18 | External risk register revised after the instructor's feedback (12 Oct).

## Holidays
Date | Holiday
2026-09-24 | Local holiday | Add any further non-working day in column A; all working-day formulas use rows 2–40.
2026-10-12 | National holiday